## Sheet1
Project name: |  | Team number and members:
Stage | What the program will do | How we plan to test it | expected completion date | actual completion date
1 | Working window layout | Visually | 2007-01-07 | 2008-01-07
2 | Allow user to select difficulity | Junit | 2007-01-07 | 2008-01-08
3 | Grid of Jbuttons | Visually | 2007-01-08 | 2008-01-07
4 | Working squares class | Junit testing | 2007-01-08 | 2008-01-07
5 | Each square knows how many bombs are around it and where they are | Junit | 2007-01-08 | 2008-01-09
6 | When square is clicked proper number is displayed or game ends if square has a bomb | Visaully | 2007-01-09
7 | Working Board Class - Knows correct sizes for each difficulity setting | Junit testing | 2007-01-09 | 2008-01-08
8 | Board knows where every square is - 2D array | junit | 2007-01-09 | 2008-01-08
9 | Check for win function | junit | 2007-01-10
10 | Check for loosing function | junit | 2007-01-10
11 | Board keeps track of number of wins | junit / command line printing | 2007-01-10
12 | Tie square class to Jbuttons | Junit and physical clicking | 2007-01-11 | 2008-01-08
13 | First button clicked cannot be a bomb | visually | 2007-01-11
14 | Reset button | visually / junit / command line printing | 2007-01-12
15 | Code to make reset button work | junit | 2007-01-12
16 | Custom board size | junit | 2007-01-12
17 | Keeping track of elapsed time | junit | as time allows
18 | Different left and right click functions | junit | as time allows
19 | Question marks on squares | junit | as time allows
20 | Best times list | junit | as time allows
NEW | Cheat Functionality | Pressing 'c' and seeing if bombs show up | 2008-01-09 | 2008-01-09
NEW | Sweep function- adjacent squares with no bombs | Clicking square with 0 bombs and seeing
| revealed and proper number displayed | which squares turn a 'revealed color | 2008-01-10 | 2008-01-10