## Sheet1
Project name: Spell Checker |  | Team number and members: Team #11: Ross Hansen, David Pick Sean Kriesberg
Stage | What the program will do | How we plan to test it | expected completion date | actual completion date
1 | Make frame appear. | Run the program and see if a frame shows up. | 2008-02-05 | 2008-02-06
2 | Implement the GUI interface | Run the program and see if the frame looks the way we would like it to. | 2008-02-05
3 | Create a dictionary class | The dictionary class builds the dictionary. | 2008-02-06 | 2008-02-06
4 | Open text files into our frame | Check to see if the text files appear in our frame | 2008-02-07 | 2008-02-06
5 | Find misspelled words | Test to see if the program can pick out the misspelled words from the text. | 2008-02-08 | 2008-02-08
6 | Fix misspelled words with letters swapped | Give suggestions for misspelled words with letters swapped. | 2008-02-10 | 2008-02-08
7 | Fix misspelled words with missing letters | Program gives suggestions for misspelled words with missing letters | 2008-02-10 | 2008-02-08
8 | Fix misspelled words with added letters | Program gives suggestions for misspelled words with added letters | 2008-02-10 | 2008-02-08
9 | Add buttons that ignore, replace, or replace all occurrences. | Check buttons to see if they do the right thing when pressed. | 2008-02-11
10 | Replace the word in the text. | Test the program to see if the spell checker actually works. | 2008-02-12